## 22-11-2023
GANTT CHART - Team B
22/11/2023
Sr. No. | Activity | Details | Start Date | End date | M | T | W | T | F | S | S | M
1 | Project Specification Discussion | Project Discussion and Doubt clearing | 2023-11-12 | 2023-11-12
2 | Software Architecture | Deciding of Sofwtare architecture, Package building, | 2023-12-12 | 2023-12-12
3 | Offlne code development | Coding of Homing of both axis | 13/12/2023 | 13/12/2023
|  | Coding of Jog Limits | 13/12/2023 | 13/12/2023
|  | Auto Control Logic | 13/12/2023 | 13/12/2023
|  | Cam AutoMat For Movement | 14/12/2023 | 14/12/2023
|  | Testing Cam Automat | 14/12/2023 | 14/12/2023
4 | Code Testing | Testing Code and functions | 15/12/2023 | 15/12/2023
5 | HMI Design | Mapview designing and interlocks | 16/12/2023 | 16/12/2023
6 | Complete operation test | Testing in Both Modes using HMI | 17/12/2023 | 17/12/2023
7 | Project Hand Over | Evaluation of Project | 18/12/2023 | 18/12/2023